## Schedule
Programmer Name(s): | Kevin Lee
| Original | Original | Elapsed time at | Second | Second | Total
| Estimate | Deadline | Intermediate Schedule | Estimate | Deadline | Time
Task |  |  | Partner 1 |  |  | Partner 1
Setup, spec reading, scheduling | 1 | 2011-08-28 | 0.5 | 0.5 | Done | 0.5
Command line parser | 0.5 | 2011-08-28 | 0.5 | 0.5 | Done | 0.5
Implement linked list | 2 | 2011-08-29 | 6 | 6 | Done | 6
Insert (memman) | 2 | 2011-08-29 | 4 | 4 | Done | 4
Remove (memman) | 2 | 2011-08-29 | 0.5 | 0.5 | Done | 0.5
Print (memman) | 2 | 2011-08-30 | 0.5 | 0.5 | Done | 0.5
Testing (memman) | 1 | 2011-08-30 | 0.5 | 0.5 | Done | 0.5
Final Documentation | 1 | 2011-08-31 | 0.5 | 0.5 | Done | 0.5
Sum of tasks | 11.5 |  | 13 | 13 |  | 13
Notes:
* All estimates should be to the nearest hour or half hour.
* If you work with a partner, there is an elapsed time column for each. If you do not work with a partner, delete the second column.
* Elapsed times should be in hours, can be measured to the half hour.
* “Original Estimate” is how many hours you originally think the task will take.
* “Original Deadline” is the date that you plan to complete this task. Not all tasks should have the same deadline!
* “Elapsed time at Intermediate Schedule” is how many hours you (and your partner) have spent when the intermediate schedule is turned in.
* “Second Estimate” is how many (total) hours you estimate the task will take at the time when you submit the intermediate schedule.
* “Second Deadline” is your revised deadline for completing the task. If the task is already completed at this point, say so.
* “Total time” is the total number of hours spent on the task when you turn the project in. If you work with a partner, show this time for both.
* “Sum of tasks” row should contain sums for the columns. Make sure that you compute this correctly for each column.
* You should add to the list of tasks in this template.