## Schedule
Programmer Name(s): | Kevin Lee
| Original | Original | Elapsed time at | Second | Second | Total
| Estimate | Deadline | Intermediate Schedule | Estimate | Deadline | Time
Task |  |  | Partner 1 |  |  | Partner 1
Setup, spec reading, scheduling | 1 | 2011-09-19 | 0.5 | 0.5 | 2011-10-01 | 0.5
Command line parser | 0.5 | 2011-09-20 | 0.5 | 0.5 | 2011-10-01 | 0.5
Implement BST | 6 | 2011-09-24 | 3 | 4 | 2011-10-04 | 4
Implement PR Quadtree | 6 | 2011-09-28 | 0 | 6 | 2011-10-05 | 2
Commands for BST | 2 | 2011-09-30 | 0 | 2 | 2011-10-06 | 1
Commands for PR Quadtree | 2 | 2011-09-30 | 0 | 2 | 2011-10-06 | 7
Testing | 1 | 2011-10-04 | 0 | 1 | 2011-10-07 | 1
Final Documentation | 1 | 2011-10-04 | 0 | 1 | 2011-10-07 | 1
Sum of tasks | 19.5 |  | 4 | 17 |  | 17
Notes:
* All estimates should be to the nearest hour or half hour.
* If you work with a partner, there is an elapsed time column for each. If you do not work with a partner, delete the second column.
* Elapsed times should be in hours, can be measured to the half hour.
* “Original Estimate” is how many hours you originally think the task will take.
* “Original Deadline” is the date that you plan to complete this task. Not all tasks should have the same deadline!
* “Elapsed time at Intermediate Schedule” is how many hours you (and your partner) have spent when the intermediate schedule is turned in.
* “Second Estimate” is how many (total) hours you estimate the task will take at the time when you submit the intermediate schedule.
* “Second Deadline” is your revised deadline for completing the task. If the task is already completed at this point, say so.
* “Total time” is the total number of hours spent on the task when you turn the project in. If you work with a partner, show this time for both.
* “Sum of tasks” row should contain sums for the columns. Make sure that you compute this correctly for each column.
* You should add to the list of tasks in this template.