## Schedule
Programmer Name(s): | Kevin Lee
| Original | Original | Elapsed time at | Second | Second | Total
| Estimate | Deadline | Intermediate Schedule | Estimate | Deadline | Time
Task |  |  | Partner 1 |  |  | Partner 1
Setup, spec reading, scheduling | 0.5 | 2011-11-17 | 0 | 0.5 | 2011-12-01 | 0.5
Command line parser | 0.5 | 2011-11-18 | 0 | 0.5 | 2011-12-01 | 0.5
Modify buffer to roll over block size boundaries | 2 | 2011-11-21 | 0 | 2 | 2011-12-01 | 2
Modify memory manger to interface with new buffer | 2 | 2011-11-21 | 0 | 2 | 2011-12-02 | 2
Modify b-tree and quad-tree to interface with memory manager | 2 | 2011-11-22 | 0 | 2 | 2011-12-02 | 3
Bugfix | 2 | 2011-11-23 | 0 | 2 | 2011-12-03 | 10
Testing | 1 | 2011-11-24 | 0 | 1 | 2011-12-03 | 1
Final Documentation | 0.5 | 2011-11-24 | 0 | 0.5 | 2011-12-04 | 0.5
Sum of tasks | 10.5 |  | 0 | 10.5 |  | 19.5
Notes:
* All estimates should be to the nearest hour or half hour.
* If you work with a partner, there is an elapsed time column for each. If you do not work with a partner, delete the second column.
* Elapsed times should be in hours, can be measured to the half hour.
* “Original Estimate” is how many hours you originally think the task will take.
* “Original Deadline” is the date that you plan to complete this task. Not all tasks should have the same deadline!
* “Elapsed time at Intermediate Schedule” is how many hours you (and your partner) have spent when the intermediate schedule is turned in.
* “Second Estimate” is how many (total) hours you estimate the task will take at the time when you submit the intermediate schedule.
* “Second Deadline” is your revised deadline for completing the task. If the task is already completed at this point, say so.
* “Total time” is the total number of hours spent on the task when you turn the project in. If you work with a partner, show this time for both.
* “Sum of tasks” row should contain sums for the columns. Make sure that you compute this correctly for each column.
* You should add to the list of tasks in this template.