{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["Schedule"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":4,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Schedule","index":0,"n_rows":29,"n_cols":7,"rows_kept":29,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["Programmer Name(s):","Kevin Lee"]
[]
[]
[null,"Original","Original","Elapsed time at","Second","Second","Total"]
[null,"Estimate","Deadline","Intermediate Schedule","Estimate","Deadline","Time"]
["Task",null,null,"Partner 1",null,null,"Partner 1"]
["Setup, spec reading, scheduling",1,"2011-08-28",0.5,0.5,"Done",0.5]
["Command line parser",0.5,"2011-08-28",0.5,0.5,"Done",0.5]
["Implement linked list",2,"2011-08-29",6,6,"Done",6]
["Insert (memman)",2,"2011-08-29",4,4,"Done",4]
["Remove (memman)",2,"2011-08-29",0.5,0.5,"Done",0.5]
["Print (memman)",2,"2011-08-30",0.5,0.5,"Done",0.5]
["Testing (memman)",1,"2011-08-30",0.5,0.5,"Done",0.5]
["Final Documentation",1,"2011-08-31",0.5,0.5,"Done",0.5]
[]
["Sum of tasks",11.5,null,13,13,null,13]
[]
["Notes:"]
["* All estimates should be to the nearest hour or half hour."]
["* If you work with a partner, there is an elapsed time column for each. If you do not work with a partner, delete the second column."]
["* Elapsed times should be in hours, can be measured to the half hour."]
["* “Original Estimate” is how many hours you originally think the task will take."]
["* “Original Deadline” is the date that you plan to complete this task. Not all tasks should have the same deadline!"]
["* “Elapsed time at Intermediate Schedule” is how many hours you (and your partner) have spent when the intermediate schedule is turned in."]
["* “Second Estimate” is how many (total) hours you estimate the task will take at the time when you submit the intermediate schedule."]
["* “Second Deadline” is your revised deadline for completing the task. If the task is already completed at this point, say so."]
["* “Total time” is the total number of hours spent on the task when you turn the project in. If you work with a partner, show this time for both."]
["* “Sum of tasks” row should contain sums for the columns. Make sure that you compute this correctly for each column."]
["* You should add to the list of tasks in this template."]